## Introduction
Introduction
This self-assessment questionnaire is part of the Team Forming and Skills Toolkit. Social housing retrofit projects involving tenants in residence are complex and require the coordination of many different areas of expertise. This toolkit describes the main skills and competencies needed to develop and deliver large-scale social housing retrofit projects.
Who should use the toolkit?
The intended audience is individuals and teams engaged in the design and development of social housing retrofit programmes and who will be involved in putting together a bid for SHDF or other funding streams.
When should you use the toolkit?
This toolkit should be used as early as possible in the development of a retrofit project (or funding application) so that any shortfall between the necessary skills and those already available to you can be identified. Plugging any gaps, through recruitment, training, or outsourcing, takes a significant amount of time and effort.
This self-assessment questionnaire helps you understand the key areas of Team Forming and Skills. Where you are strong, where you are weak, and where you have gaps that you should fill.
There is one question for five elements that you score from 0 - 5.
Recommended use:
• Read the Introduction and Framework sections of the Team Forming and Skills Toolkit to understand the framework
• Review your readiness in each area, scoring yourself 0-5 for each question
• For each question, example descriptions are given for low (0-1), medium (2-3), and high (4-5) readiness. Use these as markers to estimate where you are in your journey
• If you think you are at medium readiness/completeness, but weak and edging towards low, score yourself 2. If edging towards high, score yourself 3. And so on
• These are not absolute scores, you are looking for relative strengths and weaknesses. The example descriptions are there as a guide, not a checklist
• Your answers will be displayed on the radar diagram to the right on the next tab. The pattern will guide you to areas that need attention.

## Team Forming Self-Assessment
Team forming self-assessment
Level Descriptions
Framework Section | Score 0-5 | Low: 0-1 | Medium: 2-3 | High: 4-5
(overwrite example data with your score)
Define Roles | 4 | We do not have an integrated list of the tasks in this project. | We have a generic list of tasks and roles, but it is not complete and may not include critical roles from PAS 2035. | We have a comprehensive list and understanding of the project tasks and the roles required.
Map Roles | 4 | For most of the list we are not yet sure whether we have appropriate cover. | We have a partial mapping for the task list, but it is not complete. Some of the trickier roles are undefined. | We have completed the mapping and have a definitive answer whether each task and role is covered or not.
Identify Gaps | 3 | Gap in the list are visible, but we have not yet checked that there is no one to cover that role or assigned priorities. | We are clear where the gaps are, but we have not yet prioritised them. We don't know which are the most important. | All gaps have been identified. We have prioritised those that represent the biggest risk to the project.
Bridge Gaps | 2 | We do not yet have a plan to fill the gaps. | We have decided the best approach to fill each of the critical gaps, but we have not yet taken action. We do not yet have agreed budget or an executable plan. | We have a complete, costed plan to fill all the critical gaps. We have decided the best approach and are sourcing the right people
Manage Team | 1 | We are relying on our usual project management disciplines to keep the team aligned and effective. | We have started to build an approach to maintaining alignment and effectiveness, but it is not yet formally approved or in place. | We fully recognise the importance of clarity and communications in keeping the team aligned and effective. Team support plans are in place, and we have good visibility of potential issues.
Actions to take
Mostly Low | You do not yet have a plan to create and support the team you need to deliver the project.. Make sure you have a comprehensive list of the tasks and roles (use the suggestions in Appendix 1 as a guide). Complete the mapping to identify the gaps. Decide which are the critical gaps and develop a plan to bridge them.
Mostly Medium | You are on the journey. Where you score yourself Low, use the additional resources in level 3 to improve your readiness and capability.
Mostly High | You are in good shape. You understand what skills and capabilities you need, have identified gaps and are working to fill them. If you have decided to leave some gaps unfilled, make sure you have updated the risk register. Keep working on maintaining team alignment and effectiveness through improved communications. If you think you have done enough communication - look again!